## Earned Value Management
EARNED VALUE MANAGEMENT TEMPLATE
PROJECT TITLE | Project Title Here |  |  |  | PREPARED BY | Name of PM or Other Preparer |  |  | DATE OF REPORT | 00/00/0000 |  | TIME PERIOD | 4
PLANNED VALUE – WBS IDs and Task Titles listed here will automatically populate on worksheet tabs.
WORK BRKDWN STRUCTURE | TASK TITLE | TOTAL BUDGETED COST | PERIOD
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1.1 | Task 1.1 | 1258 | 300 | 500 | 400 | 50 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
1.2 | Task 1.2 | 350 | 200 | 80 | 30 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 | Task 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4 | Task 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 | Task 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2 | Task 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3 | Task 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.4 | Task 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.5 | Task 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1 | Task 3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2 | Task 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.3 | Task 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.4 | Task 3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.5 | Task 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.6 | Task 3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.7 | Task 3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1 | Task 4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2 | Task 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3 | Task 4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4 | Task 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TBC | TOTAL BUDGETED COST | 1608 | 500 | 580 | 430 | 90 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
PV | CUMLATIVE PLANNED VALUE |  | 500 | 1080 | 1510 | 1600 | 1601 | 1602 | 1603 | 1604 | 1605 | 1606 | 1607 | 1608
ACTUAL COST
AC | CUMULATIVE ACTUAL COST |  | 900 | 1220 | 1480 | 1620 | 1621 | 1622 | 1623 | 1624 | 1625 | 1626 | 1627 | 1628
EARNED VALUE
EV | CUMULATIVE EARNED VALUE |  | 1356.4 | 1230.6 | 1363 | 520.7 | 125.8 | 125.8 | 125.8 | 125.8 | 125.8 | 125.8 | 125.8 | 125.8
PROJECT PERFORMANCE METRICS
CV | COST VARIANCE | ( EV – AC ) | 456.4 | 10.6 | -117 | -1099.3 | -1495.2 | -1496.2 | -1497.2 | -1498.2 | -1499.2 | -1500.2 | -1501.2 | -1502.2
SV | SCHEDULE VARIANCE | ( EV – PV ) | 856.4 | 150.6 | -147 | -1079.3 | -1475.2 | -1476.2 | -1477.2 | -1478.2 | -1479.2 | -1480.2 | -1481.2 | -1482.2
CPI | COST PERFORMANCE INDEX | ( EV / AC ) | 1.5071 | 1.0087 | 0.92095 | 0.32142 | 0.077606 | 0.077559 | 0.077511 | 0.077463 | 0.077415 | 0.077368 | 0.07732 | 0.077273
SPI | SCHEDULE PERFORMANCE INDEX | ( EV / PV ) | 2.7128 | 1.1394 | 0.90265 | 0.32544 | 0.078576 | 0.078527 | 0.078478 | 0.078429 | 0.07838 | 0.078331 | 0.078283 | 0.078234
EAC | ESTIMATED COST AT COMPLETION |  | 1066.9419 | 1594.1492 | 1746.0308 | 5002.8039 | 20719.9364 | 20732.7186 | 20745.5008 | 20758.283 | 20771.0652 | 20783.8474 | 20796.6296 | 20809.4118
CLICK HERE TO CREATE EARNED VALUE MANAGEMENT TEMPLATES IN SMARTSHEET

## Actual Cost Worksheet
EARNED VALUE MANAGEMENT TEMPLATE
PROJECT TITLE | Project Title Here |  |  |  | PREPARED BY | Name of PM or Other Preparer |  |  | DATE OF REPORT | 00/00/0000 |  | TIME PERIOD | 4
ACTUAL COST – Enter amount of actual costs incurred for each task per period.
WORK BRKDWN STRUCTURE | TASK TITLE | TOTAL BUDGETED COST | PERIOD
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1.1 | Task 1.1 | 1258 | 100 | 300 | 200 | 100 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
1.2 | Task 1.2 | 350 | 800 | 20 | 60 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 | Task 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4 | Task 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 | Task 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2 | Task 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3 | Task 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.4 | Task 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.5 | Task 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1 | Task 3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2 | Task 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.3 | Task 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.4 | Task 3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.5 | Task 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.6 | Task 3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.7 | Task 3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1 | Task 4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2 | Task 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3 | Task 4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4 | Task 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AC | ACTUAL COST |  | 900 | 320 | 260 | 140 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| CUMULATIVE ACTUAL COST |  | 900 | 1220 | 1480 | 1620 | 1621 | 1622 | 1623 | 1624 | 1625 | 1626 | 1627 | 1628

## Earned Value Worksheet
EARNED VALUE MANAGEMENT TEMPLATE
PROJECT TITLE | Project Title Here |  |  |  | PREPARED BY | Name of PM or Other Preparer |  |  | DATE OF REPORT | 00/00/0000 |  | TIME PERIOD | 4
CUMULATIVE EARNED VALUE – For each Task per Period, enter the Percentage Complete.
WORK BRKDWN STRUCTURE | TASK TITLE | TOTAL BUDGETED COST | PERIOD
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1.1 | Task 1.1 | 1258 | 80% | 70% | 100% | 40% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
1.2 | Task 1.2 | 350 | 100% | 100% | 30% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
1.3 | Task 1.3 | 0 | bar: PERIOD 1 to PERIOD 12
1.4 | Task 1.4 | 0 | bar: PERIOD 1 to PERIOD 12
2.1 | Task 2.1 | 0 | bar: PERIOD 1 to PERIOD 12
2.2 | Task 2.2 | 0 | bar: PERIOD 1 to PERIOD 12
2.3 | Task 2.3 | 0 | bar: PERIOD 1 to PERIOD 12
2.4 | Task 2.4 | 0 | bar: PERIOD 1 to PERIOD 12
2.5 | Task 2.5 | 0 | bar: PERIOD 1 to PERIOD 12
3.1 | Task 3.1 | 0 | bar: PERIOD 1 to PERIOD 12
3.2 | Task 3.2 | 0 | bar: PERIOD 1 to PERIOD 12
3.3 | Task 3.3 | 0 | bar: PERIOD 1 to PERIOD 12
3.4 | Task 3.4 | 0 | bar: PERIOD 1 to PERIOD 12
3.5 | Task 3.5 | 0 | bar: PERIOD 1 to PERIOD 12
3.6 | Task 3.6 | 0 | bar: PERIOD 1 to PERIOD 12
3.7 | Task 3.7 | 0 | bar: PERIOD 1 to PERIOD 12
4.1 | Task 4.1 | 0 | bar: PERIOD 1 to PERIOD 12
4.2 | Task 4.2 | 0 | bar: PERIOD 1 to PERIOD 12
4.3 | Task 4.3 | 0 | bar: PERIOD 1 to PERIOD 12
4.4 | Task 4.4 | 0 | bar: PERIOD 1 to PERIOD 12
EV | CUMULATIVE EARNED VALUE |  | 1356.4 | 1230.6 | 1363 | 520.7 | 125.8 | 125.8 | 125.8 | 125.8 | 125.8 | 125.8 | 125.8 | 125.8